## TEST CASE
Product Name |  | Bangla Shoppers | TC Start Date | 21/12/2023 | TC Execution Start Date |  |  | TEST CASE
Module Name |  | Sign Up and Sign In | TC End Date | 22/12/2023 | TC Execution End Date |  |  | PASS | 37
Epic |  |  | Test Case Developed By | Kh. Tanveer Iftekhar | Browser (tested) | Yes |  | FAIL | 11
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) |  |  | Not Executed | 0
Test Executed by | [7 empty] | Out of Scope | 0
TEST CASE OF BANGLA SHOPPERS WEBSITE | [7 empty] | TOTAL | 48
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the Website URL in different browsers | Should run in different browsers | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'Bangla Shoppers' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Sign Up | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Check the font, text color and style |  |  | Passed
4 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Check red asterisk beside mandatory field |  |  | Passed
5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Hover over every fields |  |  | Passed
6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Check alignment of the fields |  |  | Passed
7 |  |  |  | Checkbox beside 'Sign Up for Newsletter' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Check checkbox beside 'Sign Up for Newsletter' |  |  | Passed
8 |  |  |  | Checkbox beside 'Remember Me' | Checkbox should be present on that particular field | There is no 'Remember Me' field | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Check checkbox beside 'Remember Me' | No "Remember Me" Field |  | Failed
9 |  | Functional Testing |  | Verify all fields by clicking on the Register button without any input | Sholud not allow user to register | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3.Keep mandatory fields blank 4. Click "Register" button |  |  | Passed
10 |  |  |  | Verify First Name and Last Name field is not case sensitive | Should accept the provided input | Found as per expectation | DaVid WhiTE | 1. Goto the URL https://www.banglashoppers.com/ 2. Input DaVid and WhiTE in First Name and Last Name field |  |  | Passed
11 |  |  |  | Entering space and fullstop between alphabets for First Name and Last Name | Should accept the provided input | Found as per expectation | Mr. David White | 1. Goto the URL https://www.banglashoppers.com/ 2. Input Mr. David and White in First Name and Last Name field |  |  | Passed
12 |  |  |  | Entering Space at first position in firstname and lastname field | Should not accept the provided input | Not Found as per expectation | Mr. David White | 1. Goto the URL https://www.banglashoppers.com/ 2. Input Mr. David and White in First Name and Last Name field with the blank space. 3. click "Register" button | Blank Space Accepted |  | Failed
13 |  |  |  | Checking alert message for all mandatory fields | Should pop an error message | found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3.Keep mandatory fields blank 4. Click "Register" button |  |  | Passed
14 |  |  |  | Verify the given text can be copy and paste in the name fields | Should accept the provided input | Found as per expectation | Mikel | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. input a name "Mikel" and copy-paste it to other field |  |  | Passed
15 |  |  |  | Verify firstname and lastname with special characters | Should not accept the provided input | Not found as per expectation | $$$$ #### | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter special characters in firstname and lastname field | Special character error |  | Failed
16 |  |  |  | Verify firstname and lastname with Numeric value | Should not accept the provided input | Not found as per expectation | 123 456 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter numbers in firstname and lastname field | Numeric value problem |  | Failed
17 |  |  |  | Verify firstname and lastname with decimal numbers | Should not accept the provided input | Not found as per expectation | 11.22.23 12.22.23 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter decimal numbers in firstname and lastname field | Decimale value problem |  | Failed
18 |  |  |  | Verify firstname and lastname with alphanumeric characters | Should accept the provided input | Found as per expectation | tanvir 12 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter alphanumeric characters in name field |  |  | Passed
19 |  |  |  | Inputing firstname and lastname with alphabets | Should accept the provided input | Found as per expectation | Tanvir Ifti | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter alphabets in firstname and lastname field |  |  | Passed
20 |  |  |  | Verify comma between alphabets for firstname and lastname | Should not accept the provided input | Not found as per expectation | KH,,, tan,,vir | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter comma alphabets in firstname and lastname field | Comma error |  | Failed
21 |  |  |  | Checking newsteller checkbox | Should function successfully | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Select the newsteller checkbox |  |  | Passed
22 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation with an error message | tvir671@gmail.com | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill the email address with already registered email |  |  | Passed
23 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Found as per expectation with an error message | abc@abc.com | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill the email address with invalid email address format |  |  | Passed
24 |  |  |  | Checking by inputing valid email format | Should accept the provided input | Found as per expectation | tvir671@gmail.com | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill the email address with valid email address format 4. Click Register |  |  | Passed
25 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | aB12345678 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on register button at the right corner 3. enter password to check its masking or not |  |  | Passed
26 |  |  |  | Input data to all the fields and leave the "password" and "Confirm Password" fields blank | Should display an error message | Found as per expectation | Kh Tanveer tvir671@gmail.com Male *********** *********** | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill all the valid input and no input in password section 4. Click Register |  |  | Passed
27 |  |  |  | Input only numbers in the password field | Should not allow the user to register | Found as per expectation | 12345678 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill only number value in password section 4. Click Register |  |  | Passed
28 |  |  |  | Verifying the combination of upper case and lower case letter as a password | Should allow the user to register | Found as per expectation | AbcDefGh | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill upper case and lower case value in password section 4. Click Register |  |  | Passed
29 |  |  |  | Verifying special character as password | Should not allow the user to register | Found as per expectation | ####^^^^ | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill with only special Character value in password section 4. Click Register |  |  | Passed | Minimum two type of classes required in password section
30 |  |  |  | Verify the combination of alphanumeric values and special characters as a password in the password field | Should accept the provided input as a password | Found as per expectation | Abc##123 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Input alphanumeric values and special characters in password section 4. Click Register |  |  | Passed
31 |  |  |  | Verifying the password view functionality is given or not | Should be given the "eye" icon for password view functionality | Found not as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Check the password section | No Eye button |  | Failed
32 |  |  |  | Verify the password field displays the minimum length of the password | Should display a message so that the user provide at least the minimum length of password | Found as per expectation | A123 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill without minimum password length in password fields 4. Click Register |  |  | Passed | Minimum 8 character required
33 |  |  |  | Verify whether the text can be copied and pasted from "password" field to the "confirm password" field | Should not allow the copy and paste functionality in between the "password" field an the "confirm password " fields. | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill the password then copy paste to Confirm Password section |  |  | Passed
34 |  |  |  | Checking registration with invalid email address | Should not allow user to register and pop an error message | Not found as per expectation | Firstname: Mr Lastname: White Email: Asd!@gm.com Password: 9876543AA Confirm Password: 9876543AA | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill invalid email 4. click Register | Invalid E-mail Accepted |  | Failed
35 |  |  |  | Checking registration button with valid credentials | Should allow user to register | Found as per expectation | Firstname: Mr. Lastname: White Email: tvir671@gmail.com Password: 9876543AA Confirm Password: 9876543AA | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill valid email 4. click Register |  |  | Passed
36 |  |  |  | Checking confirmation mail sent to the registered email | Should Sent successfully | Found as per expectation | Firstname: Mr. Lastname: White Email: tvir671@gmail.com Password: 9876543AA Confirm Password: 9876543AA | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill all the fields with valid credential 4. click Register |  |  | Passed
37 |  |  |  | Checking confirmation Pop up message when registration is done | Should Shown properly | Found as per expectation | Firstname: Mr. Lastname: White Email: tvir671@gmail.com Password: 9876543AA Confirm Password: 9876543AA | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill all the fields with valid credential 4. click Register |  |  | Passed | Very few seconds appeared
38 |  |  |  | Checking 'Sign in with Facebook' | Should allow user to register | Found as per expectation | Click on 'Sign in with Facebook' | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Click on the Facebook field | Error page appeared |  | Failed
39 |  |  |  | Checking 'Sign in with Google' | Should allow user to register | Found as per expectation | Click on 'Sign in with Google' | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Click on the Google field |  |  | Passed
40 |  | Usability Testing |  | Checking copy paste functionality in every field Except Password section | Should copy and paste text from fields | Functioning successfully | TANVEER | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. check all the fields with data by copy paste |  |  | Passed | only password section doesn't allow to Copy-Paste for Safety
41 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | click tab | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. check all the fields with tab button of keyboard |  |  | Passed
42 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | click enter | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Input Enter in every field |  |  | Passed
44 |  | UI Testing | Sign In | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corne |  |  | Passed
45 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corne |  |  | Passed
46 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corne |  |  | Passed
47 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corne |  |  | Passed
48 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corne |  |  | Passed
49 |  |  |  | Checkbox beside 'Sign Up for Newsletter' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corne |  |  | Passed
50 | [7 empty] | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corne
43 |  | Functional Testing |  | Verify all fields by clicking on the Login button without any input | Should not allow user to login | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Login button at the right corner 3. click Login |  |  | Passed
44 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | aB12345678 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Login button at the right corner 3. enter password to check masking |  |  | Passed
45 |  |  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation | tvir%%@l.c 123 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Login button at the right corner 3. enter wrong email and password 4 click login |  |  | Passed
46 |  |  |  | Checking login valid credentials in email and password field | Should allow user to Login | Found as per expectation | Email: tvir671@gmail.com Password: A1234567 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Login button at the right corner 3. enter valid credential to the fields 4. click login |  |  | Passed
47 |  |  |  | Verifying ‘Forgot your Password’ functionality | Should sent an email for recovering password | Not Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Login button at the right corner 3. click the option named 'Forgot your password | not provide any further action |  | Failed | loading for a long time
48 |  |  |  | Verifying the password view functionality is given or not | Should be given the "eye" icon for password view functionality | Not Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3. Check the password section | No eye button |  | Failed
49 |  |  | Improvement Scopes | 'Remember Me' checkbox should beIncluded
50 |  |  |  | Registration Successful message should displayed more time
51 |  |  |  | Fix Forgot Password section
52 |  |  |  | Login page should also have red asterisk marked to the email and password field